## Rexlio Task Tracker
Phase | Modification/ Upgrade Task | Status | Priority | Remark
A | Table selection popup — remove image, show table name only | Done (then reverted) | Low | Implemented via scoped CSS override (#show_tables_modal2); could not edit DB-stored floor-plan markup directly. Later REVERTED per decision to keep original table images.
A | Order print-out (KOT) price display | Undone / Backlogged | Low | Deprioritized — invoice already shows price correctly. No action taken.
B | List Item (Ingredient) screen filters — name/code, category, purchase unit, consumption unit, Type | Done | Medium | Extra: found and fixed a cross-tenant data leak bug in keyword search grouping while building this.
B | List Purchase & Purchase Report filters — date range, supplier, payment status, category, item | Done | Medium | Shared filter logic built once (Purchase_model::getFilteredPurchases) and reused by both screens. Payment status derived from tbl_purchase.due, not a true settled status.
B | Stock Report — new screen (Report/stockReport) | Done | Medium | Extra: added ~25 missing DB indexes (none existed before) with tested rollback; fixed a legacy broken unit-display string hack. Major finding pushed to Phase E: tbl_ingredients mixes true ingredients and auto-generated product rows (is_direct_food split).
C | Dedicated Running Order screen | Done | High | Major finding: running orders don't exist in tbl_sales at all — live in tbl_kitchen_sales/IndexedDB. Only Order Details works fully server-side; other 5 actions deep-link into POS. Accepted limitation: deep-link only works on same device/user who placed the order.
C | Dedicated Table screen | Done | High | Found and fixed a second bug: non-deterministic guest-count dedup on duplicate booking rows.
C | [Issue found during Table screen testing] Completed orders never syncing to tbl_sales | Done — fixed | Critical | BASE-PRODUCT DEFECT (confirmed vendor-identical, not Rexlio-introduced). Root cause: unguarded JSON.parse in push_online()/push_online_sync() silently killed the entire sync loop on one malformed row. Fixed with guard-then-parse + try/catch. This means product sales reports now reflect real data going forward.
D | Add VIP price and Club price tiers to items | Done | High | Delivered as two independently split tiers after iteration (see remarks below) — originally a single combined 'VIP¦Club' button, later split at user's request.
D | Rename Dine In → Regular, Take Away → Outlet | Done | Low | Confirmed display-only via exhaustive search before renaming. Non-English (French/Spanish/Arabic) language files deliberately left untranslated — flagged for human decision.
D | Counter-level default price tier assignment, manually overridable | Done — redesigned mid-phase | High | Simplified twice: ended as a full COUNTER-LEVEL LOCK — non-Admin/Manager staff get the entire order-type row fixed to the counter's assigned tier, no override. Admin/Manager retain full override.
D | [Extra] price_tier vs order_type architecture decision | Done | High | Major finding: order_type was doing double duty (fulfillment + pricing + table-gating). Built a separate price_tier field so 17 table-gating sites needed zero changes.
D | [Extra] Table-gating consistency bug | Done — fixed | Medium | Found pre-existing inconsistency: click-handler disabled tables for Take-away while order-load path enabled it. User decided Take-away should allow tables; both paths made consistent.
D | [Extra] VIP¦Club single-button → two-button split | Done | Medium | User reconsidered 'keep it simple' decision and asked for full split. Corrected an earlier misdiagnosis: counter-lock was never broken — real causes were a hardcoded tier-4 button and missing Club prices.
D | [Extra] Footer/layout regression (Cancel/Draft/Quick Invoice/Place Order buttons disappearing) | Done — fixed twice | High | Hardcoded CSS grid (repeat(4,1fr)) broke when button count grew. Fixed at 5 buttons, then pre-emptively re-fixed at 6 buttons for the VIP/Club split. Root cause: setHeightInComponent() exists to auto-compensate but is dead code, never called — documented as a standing fragility for any future 6th+ button.
D | [Extra] 6-role permission system | Done | High | New request mid-phase. Roles created: Admin, Manager, Cashier, Waiter, Store Officer, Accountant. Full access matrix applied directly (test environment, no live impact).
D | [Extra] Register-integrity bug — waiters placing orders / opening registers with no register open | Done — fixed | Critical | MAJOR FINDING, confirmed base-product defect (vendor-identical). Register check was UI-only — actual order-writing endpoints had ZERO register check for ANY role. Found LIVE in production (a waiter had a register genuinely open). Fixed at both UI and persistence layers. push_online() late-completions deliberately NOT blocked, to avoid stranding paid orders.
D | [Extra] Register-opening restricted to Admin/Cashier/Manager | Done | High | Built as a configurable role permission (not hardcoded), consistent with the 6-role system above.
D | [Extra] Waiter self-visibility + PIN verification | Done | High | Waiters now see only themselves in waiter-selection; Cashier/Manager selecting another waiter must enter that waiter's PIN (Admin exempt, per user decision). Server-side re-verification at save time blocks DOM-tampering bypass. Existing PIN mechanism (tbl_users.login_pin) reused — no new field needed. Flagged: PINs stored in plaintext (pre-existing, not fixed) and no rate-limiting (deterrent-level only).
D | Admin UI to toggle individual price tiers on/off | Not done — deferred | Low | DROPPED in favor of the counter-lock design: a client who doesn't use a tier simply never assigns it to any counter. Documented as intentionally dropped, not forgotten. A system-wide toggle remains a future option if ever needed.
D | Wiring up setHeightInComponent() as the durable layout fix | Not done — deferred | Medium | Worked around twice via direct CSS grid fixes instead. Needs a live POS login to verify safely; flagged as future hardening.
D | French/Spanish/Arabic translations for Regular/Outlet renames | Not done — deferred | Low | Client terminology choices, not auto-translated. Needs a human translator.
E | Rename 'Ingredient' → 'Item' throughout the UI | Done | Medium | User wanted precise split-aware labeling but explicitly asked to avoid a long/costly process. Investigation showed split-aware would be MORE work for LESS consistency (41 of 46 locations had no per-row data to split on) — recommended and used blanket rename (Option B) instead. Landmine found and avoided: tbl_ingredients.ing_type stores the literal string 'Plain Ingredient' as real data in WHERE clauses — rename confined strictly to lang() values, never touched data.
E | [Extra] food_type_tooltip string | Done — deliberately excluded | Low | One string deliberately NOT renamed — 'ingredients' there means recipe components, a different concept; forcing the rename would have produced nonsense text.
E | [Extra] CRLF line-ending damage from sed tool | Done — fixed | Medium | Self-caught: the rename script silently converted the language file from CRLF to LF. Restored before finalizing so version control diffs stay content-only.
E | [Note] Duplicate ingredient_category language key found | Not done — flagged only | Low | Pre-existing, unrelated dead duplicate key. Harmless as-is (second definition wins). Worth cleaning up sometime, not scheduled.
F | F0 — Verification harness (scratch DB, no production changes) | Done | High | Found 5 issues purely from building test fixtures: no del_status filter on recipe consumption (latent), food-menu items with no recipe can never be stock-blocked, real production stock already negative (settles oversale default), 19 stranded test orders found, a minor future-proofing note on new product types.
F | [Extra] Security hole — Custom::encrypt_decrypt() global no-op | Done — scoped fix, wider issue documented | Critical | Confirmed vendor design (byte-identical to extracted vendor package), not a nulling artifact. F1 fixed only setOutletSession(), since that's what Central Store depends on. Every OTHER controller using the same 'encrypted id' pattern (Transfer, Purchase, FoodMenu, Ingredient, Outlet) remains equally exposed — documented as a known systemic gap, deliberately not expanded into Phase F.
F | 19 stranded open test orders from Phase C testing | Done — cleared | Medium | Confirmed genuine test data (both waiter fixture accounts, correct dates/outlet, no completed sale). Cleared via the product's own cancellation path before F1 began, to avoid corrupting F3's first real test.
F | F1 — Central Store outlet creation + access control | Done | Critical | Central Store outlet created, sales blocked there (is_sales_enabled flag). setOutletSession() membership hole closed — closes the wider security gap for outlet-switching specifically. Default-deny added for users with no outlet assignment. Central Store restricted to Admin/Manager/Accountant.
F | [Extra] 3 self-found bugs during F1 build | Done — fixed | High | A latent PHP 8 fatal (Admin passing check for non-existent outlet id), an infinite redirect loop (blocked users bouncing between two guards), and a guard-ordering problem (Admin wrongly prompted to open a register at Central Store). All 3 caught and fixed before being reported as complete.
F | [Flagged, not built] Register can still be opened at Central Store via direct URL | Not done — flagged only | Low | Low priority — grants nothing meaningful since POS sales stay blocked regardless. Left as a documented loose end.
F | F2 — Outlet filtering on Item/Stock screens (Inventory, Alert List, Stock Report) | Done | High | 'All Outlets' correctly scoped to only outlets the user can access (not company-wide), preserving F1's access restrictions. Arithmetic verified exact (All Outlets = sum of individual outlets).
F | [Extra] Security hole — Report::stockReport() unvalidated outlet_id POST | Done — fixed | Critical | Second real vulnerability found, this one introduced during this project's own earlier Phase B work (not vendor code). Any user could POST an arbitrary outlet id and read its stock report. Fixed as part of F2.
F | [New request] Outlet filter + Stock Qty/Unit Selling Price columns on List Item | Done | Medium | User flagged List Item had no outlet filter after F2 shipped. Investigation found List Item had NOTHING outlet-dependent to filter on at all — resolved by pulling forward Stock Qty column from the future enhancement list (user's chosen option) rather than shipping an inert dropdown. Unit Selling Price added but renders blank on current data (no direct-sale products exist yet) — correct, not a bug.
F | [Extra] Shared stock-formula extraction | Done | Medium | Found the same 11-term stock arithmetic duplicated in 4 places in the codebase. Extracted into one shared helper, verified behavior-preserving against all 4 original call sites.
F | [Bug found, not fixed] Inventory screen stock VALUE figure is mathematically wrong | Not done — deferred, documented | High | String-concatenation bug (whole units + remainder treated as decimal digits) instead of proper division — understates/overstates stock value. Displayed quantity text is correct; only the value float is wrong. Deliberately left untouched (a number the user may have reconciled against) — scheduled to be fixed when Stock Value columns are built in the next phase.
F | F3 — Committed stock calculation (closes the 'auto-deduct' timing gap) | Done | High | User proposed real-time deduct-on-placement instead; investigated and confirmed staying with the safer committed-calculation approach (real-time writes risked double-counting against existing completion logic). Deliberately reproduces a known del_status omission quirk from the existing consumption writer, to avoid permanent drift between the two.
F | [Extra] window.items now carries live available_units per item | Done | Medium | Deliberately scoped to the counter's OWN outlet only (never 'All Outlets') on the sale screen — the concrete fix for 'Central Store running dry should never stop a bar selling stock it already has locally.'
F | F4 — Oversale admin control (global default + per-item override) | Done | High | Confirmed real production data already has negative stock — global default set to 'Yes' so the feature is a true no-op on install. Self-found and fixed a fail-closed bug in its own first draft (malformed values were blocking sales instead of allowing them) before shipping.
F | [Decision deferred] Variation inheritance of oversale policy | Not done — deferred, guidance captured | Low | Variations don't currently inherit a parent item's block/allow policy. User's guidance for when this is picked up: the PARENT holds the real stock data, so a blocked parent's variations should follow the parent's block.
F | F5 — Zero-stock block (client + server enforcement) | Done | Critical | Client + server enforcement of the zero-stock block, built on the F3 available_units convention and the F4 oversale_block flag, correctly distinguishing '' (no recipe = unconstrained) from '0' (genuinely out of stock). Blocks on the SELLING outlet's stock only, per the corrected requirement. User-confirmed working; this row was left at 'In Progress' after that confirmation and is now flipped to Done - status/remark edited in place, no other row touched.
F | F6 — Transfer system gaps (in-transit visibility, unused received-ingredients table) | Not done — deferred | Medium | Explicitly out of scope for Phase F; orthogonal to items 14/15/17. Two real gaps documented: stock in transit is invisible everywhere, and tbl_transfer_received_ingredients is read by 4 ledger queries but never written to by any code path (vestigial).
Next | List Item — Stock Value by Purchase Price column | Not started | Medium | Queued for the phase immediately after Phase F completes.
Next | List Item — Stock Value by Selling Price column | Not started | Medium | Blocked on fixing the Inventory valuation math bug found in F2 first.
Next | Bulk upload of NEW items | Not started | Medium | Format/approach (CSV/Excel, create-only vs. updates too) to be investigated and proposed when this phase starts.
Next | Bulk UPDATE of existing stock quantities (download current qty, fill new qty, re-upload) | Not started | Medium | New request — distinct from bulk item upload. Admin-only, locked from all other roles.
Next | List Food Menu — search/filter by name | Not started | Low | Believed genuinely missing; not yet verified against current code.
Future | Owner's Mobile App | Not started / Not scoped | Low | Needs a dedicated planning discussion. Open questions: native app vs. mobile web view, auth reuse, read-only vs. actions, whether the existing Waiter Panel pattern is a relevant precedent.
Future | Dashboard Enhancement — running order value, today's sales all outlets, outlet/register filter | Not started / Not scoped | Medium | Directly relevant to a gap found in F2: the dashboard alert badge currently disagrees with the Alert List in All-Outlets mode.
Future | WhatsApp End-of-Day Sales Notifications | Not started | Low | Free/unofficial route (Baileys) planned first, official Meta Cloud API added later behind a provider-agnostic interface.
Future | Web Push Notifications for Waiter Panel | Not started | Low | Browser-based via service worker, no native app required.
Deferred | Hotel Operations Add-on Module | Done - built and live | Low | BUILT. Housekeeping + Front Desk delivered as an isolated add-on behind the module switch. Schema migration 2026-09-16_02, stay value 2026-09-17_01, reports permission 2026-09-17_02. Controller application/controllers/Hotel.php, views application/views/hotel. Documented in doc/HOTEL_OPERATIONS_GUIDE.md and doc/GO_LIVE_HOTEL_2026-09-16.md. Reservations and Guest Folio remain out of scope.
Final | Branding & License Cleanup | Not started | Low | Remove CodeCanyon/iRestora PLUS references, apply Rexlio branding within White Label rights only. Does NOT include license/activation bypass — separate legal matter. Custom anti-copy protection to be added separately.
Report | [Bug found, not fixed] slick carousel fails to initialise on every report screen | Not done - flagged only | Medium | $(...).slick is not a function at new_ui_design.js:101, present on every report screen. Same root cause shape as the jQuery instance ambiguity found while building the invoice popup: report pages load jQuery TWICE (userHome head, then again inside the report view), then custom_report.js calls $.noConflict(), handing window.$ back to the FIRST instance. slick.min.js registers .slick on the instance current at userHome:1112, but new_ui_design.js at :1113 calls it through $, which by then points elsewhere. Pre-existing, NOT caused by the report batch. Deliberately out of scope for that batch. Likely fix is to bind the affected scripts to window.jQuery explicitly rather than $, but it touches shared layout JS used by every screen including the POS, so it needs its own isolated stage and verification.
Report | [Base-product defect] push_online() update branch hardcodes a Cash payment row, double-counting non-cash sales | Done - fix applied to production | Critical | LIVE FINANCIAL DATA-INTEGRITY BUG, now FIXED in Sale::push_online(). Confirmed VENDOR code, not introduced by Rexlio work. Investigation corrected one point from the original write-up: the getPaymentInfo() guard is inside push_online() itself (2574/2592), NOT in update_order_status_ajax(), which is a separate and correctly-written method. Sale.php is the ONLY file that writes tbl_sale_payments (10 sites, all classified); every reference in Report_model, Sale_model, Dashboard_model and my_helper is a read. TWO failure modes were found in the same lines, reached by different callers with different payloads. MODE A (re-sync, push_online/push_online_sync): payload has payment_object, so the hardcoded Cash row AND the real row both survive - revenue double-counted; masked when the real method is Cash because the guard matches. MODE B (edit an existing paid sale via push_online_update, pos_script_v7.3.js:8939): that payload carries NO payment fields at all, so the delete at 2360 destroyed the real rows, the hardcoded Cash row replaced them, the real writer never ran, and paid_amount/due_amount/payment_method_id were written as 0 from absent fields. Mode B is the worse of the two - totals still reconcile, so the 'payments sum equals total' check cannot detect it. MODE B WAS CONFIRMED TO HAVE FIRED IN PRODUCTION on sales 1004 and 1005 (real POS and Bank Transfer tenders hard-deleted, no recovery trail). FIX: the update branch no longer deletes payment rows and no longer inserts the hardcoded Cash row; the pre-writer delete now fires only when the request actually supplies replacement payment data; and on the edit path payment_method_id/paid_amount/due_amount are no longer overwritten from absent fields. Decision B1 (user): preserve the payment record as-is on an edit, never auto-rescale - an edit is not a re-tender, and post-payment edits are rare and Manager/Admin-only. B1 needed one piece of extra wiring that the original design missed: due is driven ENTIRELY by tbl_sales.due_amount (getCustomerDue, Customer Due Report, Customer Ledger, and the R3 Due filter all read it), so the fix recomputes paid_amount from the surviving payment rows and sets due_amount = total_payable - paid_amount. That routes any post-edit shortfall into the EXISTING Customer_due_receive flow instead of fabricating a payment. Negative due (edit lowers the total) is deliberately NOT clamped - it is a genuine customer credit; due reports filter due_amount > 0 and ignore it. VERIFIED on a scratch clone (rexlio_pw) with a separate app tree (application_pw) and a hard interlock, driving the REAL controller over HTTP - 31/31 checks across 3 stages. Both defects reproduced before the fix and gone after; Cash control unaffected; insert path unchanged; replaying all 19 stored payloads leaves payment rows identical to baseline; payment total 20,267.50 unchanged; Z-Report, Register Report and all four R6 popups hash-identical; register 1's stored {"Cash":8127} snapshot untouched. Production file is byte-identical to the verified build. All scratch artifacts removed.
Report | R1 – Column visibility (ColVis) on report screens | Done | Medium | Runtime-guarded implementation. A static 'colvis' entry in the shared button list would have thrown 'Unknown button type' and aborted DataTable init on all 24 screens still on Buttons 1.5.2 (which does not ship colVis); caught before shipping and rebuilt so the button is appended via .concat() only when the loaded Buttons build actually provides it. Screens on 1.7.0 get ColVis; the rest are untouched and unbroken.
Report | R2 – Shared invoice-detail popup (Sale No click) | Done | High | New Report::invoiceDetailsAjax() + Report_model::getInvoiceHeaderForPopup(), rendered by frequent_changing/js/report_invoice_popup.js. Two environment constraints discovered and worked around: report pages load jQuery twice and custom_report*.js calls $.noConflict() (so the script binds to window.jQuery, not $), and Bootstrap here is 5.0.1 which has Modal.getInstance() but NOT getOrCreateInstance() (added in 5.1) - the first live failure. Access chain registered under controller 378 falling back to 167.
Report | R3 – Detailed Sale Report gaps (invoice no, Due filter, All Outlets, payment outlet) | Done | High | Added invoice-number (sale_no) filter, a working Due-status filter, All-Outlets scope and a Payment Method filter to Report_model::detailedSaleReport(). The 'All Due' filter previously returned paid sales. While testing this, the phantom-Cash payment bug (row 57) surfaced - investigated to root cause and confirmed a base-product defect rather than a reporting fault.
Report | R4 – Sales by Category (rename, All Outlets, User + Time Range filters) | Done | High | Report_model::foodMenuSaleByCategories() extended with user_id, start_time/end_time and outlet_ids; kept as a category-level summary (no Customer filter, by decision). NOTE FOR RETEST: the first patch attempt was misplaced by a non-unique string match - it landed in sub_total_foods() instead, which left this report returning 0 rows always AND broke the Z-Report's food subtotal. Both were fixed: the patch was reapplied using brace-matched method boundaries with a uniqueness assertion, and sub_total_foods() was restored byte-identical to vendor. Root cause of the missed verification: the test harness re-implemented the intended SQL by hand instead of executing the shipped method, so it validated intent rather than code; later harnesses extract and execute the real method body. RETESTS NOW COMPLETE, run against the production code on a clone of current live data: Sales by Category returns correct category rows (Drinks, Soup) under the User filter, the Time Range filter and All Outlets - and a deliberately narrow window (00:00-00:01) correctly returns ZERO rows, which is the discriminating test proving the time filter is actually applied rather than ignored. Z-Report renders the correct food subtotal for two separate dates (4,000.00 on 2026-08-19 and 6,000.00 on 2026-08-14), each matching the sub_total_foods() query exactly, with no undefined-variable notices anywhere in the output - confirming the collateral damage is fully repaired.
Report | R5 – Sidebar 'Panel' entries + Order Lookup screen | Done | Medium | Sidebar entries added for Running Order and Table screens. New Order Lookup screen (Monitor::orderLookup, view monitor/order_lookup.php, Sale_model::getOrderLookup) presenting a UNION of running orders (tbl_kitchen_sales) and completed sales (tbl_sales). The two tables are disjoint by construction - kitchen rows are hard-deleted on completion - so the UNION cannot double-count. Registered as controller 378 in the Monitor access chain.
Report | R6 – Register Report 'View' popup | Done | High | New Report::registerDetailsAjax() + Report_model::getRegisterDetailsForPopup() / getRegisterProductsSold(), rendered by frequent_changing/js/register_details_popup.js. Fully separate READ-ONLY query by explicit requirement - it never touches Sale::registerDetailCalculationToShow(), which belongs to the live register-closing flow, so viewing an open register cannot disturb it. Register scope is derived as counter_id + outlet_id + a time window over tbl_sale_payments.date_time; this reproduces register 1's stored snapshot exactly. Shows the derived total and the recorded-at-close total side by side on purpose, because they can legitimately differ. Cancelled orders omitted by decision. KNOWN LIMITS documented: overlapping register windows cannot be separated by any available key (register 13 contains 14/17/20, and filtering by user_id makes it worse), and Expense/Purchase/Due-Receive/Supplier-Payment are dated by day not timestamp, so a part-day register shows whole-day figures - stated in the popup itself, not just in docs. Final bug: the View button rendered and fired when clicked programmatically but was not the hit target for real mouse clicks (no pointer cursor). The DataTables scroll-clone theory was investigated and DISPROVED (this page sets no scrollX/fixedHeader, so no clone exists); fixed by giving the Actions cell and button an explicit stacking context plus pointer-events/cursor, scoped to this view. User-confirmed working.
Report | Report enhancements batch (R1–R6) – overall status | Done | High | Batch closed by R6, its highest-risk item. Delivered: R1 ColVis, R2 invoice popup, R3 Detailed Sale Report gaps, R4 Sales by Category, R5 sidebar Panel + Order Lookup, R6 Register popup. Original item 6 (auto-print investigation) was DROPPED by the user, resolved independently. Scope was reporting-only and held to that. Two things came OUT of this batch rather than being fixed inside it, both correctly kept separate: the phantom-Cash payment writer defect (row 57, now the active stage) and the slick carousel failure (row 56). Outstanding within the batch: the two R4 user retests noted on that row. Also queued and deliberately not bundled: the DataTables Buttons 1.5.2 to 1.7.0 upgrade for the remaining 24 report views, which needs its own isolated stage.
Next | DataTables Buttons 1.5.2 → 1.7.0 upgrade for the remaining 24 report views | Not started | Medium | Surfaced by R1. The codebase carries TWO Buttons builds: 1.5.2 in assets/datatable_custom/ (25 views) and 1.7.0 in frequent_changing/js/dataTable/ (6 views). Only 1.7.0 ships colVis, which is why R1 had to be runtime-guarded rather than applied uniformly. Consolidating on 1.7.0 would let ColVis apply everywhere and remove the divergence, but it changes the table library under 24 live report screens, so it needs its own isolated stage with per-screen verification - not a drive-by.
Report | [Data correction] Sales 1004 and 1005 - real payment method destroyed by the Mode B defect | Done - soft-deleted | Critical | RESOLVED. The user confirmed both sales were their own test edits, not real transactions, so no reconstruction of the original tender was needed or attempted. Both were soft-deleted rather than hard deleted, matching how sale 1000's phantom payment row was handled: del_status='Deleted' applied to tbl_sales, tbl_sale_payments, tbl_sales_details, tbl_sale_consumptions, tbl_sale_consumptions_of_menus, tbl_sale_consumptions_of_modifiers_of_menus and tbl_orders_table. tbl_sales_details_modifiers has no del_status column, but reports reach it through tbl_sales_details, which is marked - noted so nobody later mistakes it for a missed table. A row-level rollback snapshot was taken first. Result: live sales 19 -> 17, live payment rows 21 -> 19, live payment total 20,267.50 -> 17,767.50, which is exactly minus the two sales' 1,000 and 1,500. Historical context worth keeping: these two are the only confirmed production instances of the Mode B defect (row 57), and they are why that defect was proven real rather than theoretical.
Next | [Base-product defect] tbl_sales.payment_method_id is written as Cash for every sale | Not started - scoped, own stage | High | Found while investigating row 57 and deliberately kept out of that stage by agreement. push_online line 2334 sets payment_method_id from $order_details->payment_method_type, which comes from the #finalie_order_payment_method select in the finalize modal - separate from the tender UI that builds payment_object. Checked against the stored payloads of eight sales: payment_method_type is "1" in EVERY one, including sales genuinely tendered as Credit Card (2), Bank Transfer (4) and POS (57). This affects the INSERT path too, so the column is unreliable for essentially every sale, not just re-synced ones. Sales 1000/1001/1004 read correctly today only because they were corrected by hand. Consequence: after the row 57 fix a re-sync now writes correct payment ROWS but still a wrong header column. Matters because that column drives the payment-method summary reports (Report_model 377-411, 2308) and the dashboard getSalePaidAmount(). Fix direction: derive the header from payment_object rather than from payment_method_type. Needs its own stage plus a decision on whether to backfill history, since new sales would otherwise disagree with every existing row.
Next | Due-payment visibility batch - surface negative due (customer credit) properly | Not started | Medium | Raised by the row 57 fix. due_amount can now legitimately go negative when a post-payment edit LOWERS a sale's total below what was already paid - a genuine customer credit. Deliberately not clamped to zero, because clamping silently discards money owed to the customer. It is currently invisible: every due surface filters due_amount > 0, so a credit neither shows on the Customer Due Report nor nets off correctly anywhere the user can see. getCustomerDue() does net it (it sums the raw column), so the figure is right but unexplained. Also worth folding in here: tbl_customer_due_receives has no sale_id, so collection is customer-level rather than invoice-level, and getCustomerDue() is outlet-scoped, so a due raised at one outlet is not collectable at another.
Bulk | Food Menu Bulk Upload - extended (VIP/Club, row cap, outlet reconcile) | Done - scratch verified, pending live permission | High | EXTENDED the existing vendor uploader rather than building new: FoodMenu::uploadFoodMenu / ExcelDataAddFoodmenus / asset/sample/Food_Menu_Upload.xlsx already existed, gated by the existing configurable permission upload_food_menu (tbl_access id 241). Changes: (1) VIP and Club price columns added at O/P - appended rather than slotted beside the other prices on purpose, because inserting them mid-sheet would shift image/loyalty/alternative-name and silently corrupt any file built from the older template; (2) row cap raised from 54 (~50 items) to 2003, still bounded because PHPExcel holds the whole sheet in memory; (3) outlet reconcile step. CORRECTION TO AN EARLIER FINDING: I first reported that imported menus would be invisible at every till until manually assigned. That was WRONG on this install. updatePrice() (my_helper.php:1512), called by the importer under isLMni() - true here because language_manifesto rot13s to 'eriutoeri' - already appends new ids to every outlet's food_menus and seeds food_menu_prices. I had skimmed that function, classified it from its first lines as price-only, and never read its tail. VERIFIED 11/11 on scratch: 5 tiers stored, items present on all 5 selling outlets, Central Store correctly cleaned, per-outlet prices seeded with 3 tiers, pre-existing menus untouched.
Bulk | Food Menu Bulk Price Update - NEW tool, outlet-scoped | Done - scratch verified, pending live permission | High | New: bulkPriceFoodMenu / downloadFoodMenuPrices / ExcelDataUpdateFoodmenuPrices, plus view master/foodMenu/bulkPriceFoodMenu.php and new configurable permission bulk_price_food_menu under parent 234. Own permission rather than reusing upload_food_menu, because creating items and repricing a live menu are different privileges. DESIGN DRIVER: pricing on this install is SPLIT. The POS reads Regular/Takeaway/Delivery from tbl_outlets.food_menu_prices (JSON, tmp{id} => 'reg¦¦take¦¦deliv') and only falls back to tbl_food_menus when the outlet has no entry; VIP and Club are never in that layer (main_screen.php:114-118) so they are global. A flat 5-column global update would therefore have changed nothing at any till for three of the five tiers. Decision A (user): outlet selector for the three per-outlet tiers, VIP/Club labelled global. The outlet id is written INTO the file and re-authorised on upload via canEnterOutlet(), so a file cut for one site cannot be applied to another. Blank cell = leave unchanged. All-or-nothing validation: a half-applied price file is worse than a rejected one. VERIFIED 15/15 on scratch including the round-trip no-op, a positive control, and a rejection control. NOTE ON TEST METHOD: the first version of the no-op test was FALSE-PASSING - a rejected upload also changes nothing, so it passed while the upload was silently failing on an expired session. Every upload now asserts the success flash.
Next | [Base-product defect] updatePrice() assigns new food menus to Central Store | Not started - own stage | Medium | Surfaced by the bulk-upload work. updatePrice() (my_helper.php:1512) appends every newly created food menu id to EVERY outlet's food_menus list and seeds food_menu_prices, with no check on whether the outlet actually sells. Central Store is a purchasing-only outlet that must never sell (the F1 rule), and it accumulates sellable items this way - proven on scratch: its list went ',5' to ',5,6,7' after an import. The bulk-upload reconcile step now corrects this for imported items specifically, but the defect remains at source and also fires from the Outlet edit screen, so any menu created or edited there still lands on Central Store. Deliberately NOT fixed inline: updatePrice() is shared vendor code with more than one caller, so it needs its own stage and its own regression pass. isSalesEnabledOutlet() already provides the correct test (Central Store is_sales_enabled=0).
Next | Rockbell menu file needs restructuring before it can be imported | Blocked - needs a transform step | High | Tested the real Rockbell_Lounge_Menu.xlsx (174 rows) end to end through the uploader on the scratch clone. READABILITY IS FINE - no Excel re-save is required. Although created by openpyxl the file was last saved by LibreOffice 24.2.7.2, and PHPExcel parses it cleanly (174 rows, all values). That matters because PHPExcel CANNOT read a pure openpyxl-written file at all - it warns in Excel2007.php:457 and returns an empty sheet - though it fails safe, rejecting rather than importing garbage. STRUCTURE IS THE BLOCKER. The file is Category ¦ Sub Category ¦ Item ¦ Variant ¦ Regular ¦ Takeaway ¦ Delivery ¦ VIP ¦ Club with headers on row 1; the template is Name ¦ Code ¦ Category ¦ Regular ¦ Takeaway ¦ Delivery ¦ Tax Name ¦ Tax % ¦ Description ¦ Veg ¦ Beverage ¦ Image ¦ Loyalty ¦ Alt Name ¦ VIP ¦ Club with headers on row 3 and data from row 4. Upload was rejected with column D/J/K errors and imported nothing. Also unmapped: there is no Code column (Code is required); Sub Category has nowhere to go because food menu categories are FLAT (no parent_id on tbl_food_menu_categories); and Variant implies variations, which the vendor template explicitly says to exclude from bulk upload. A transform step is needed, plus decisions on code generation, sub-category handling and variants.
Incident | [CRITICAL - FIXED] Waiters could not place orders on ANY order type | Done - fixed and verified | Critical | SEVERITY CORRECTED BY USER: this affects EVERY order type and EVERY waiter. It was first seen on a Club-locked counter, and my initial report wrongly scoped it as Club/counter-lock specific - the lock was incidental to where testing happened, not the trigger. Reproduced identically on local AND the fresh live Rockbell deployment. SYMPTOM: waiter selects items normally, clicks Place Order, nothing happens - no request, no message, no visible error. CAUSE: waiter self-attribution renders #select_waiter as a fixed hidden INPUT instead of <select class=select2>, but the order handlers called $('#select_waiter').data('select2').open()/.close() unguarded. For a waiter that resolves to undefined, so it threw TypeError INSIDE the .place_order_operation click handler, killing it before the request was built. jQuery does not surface it, so the button looked dead. Role-specific: Admin/Cashier/Manager get a real select2, so the same line correctly opens the prompt. SCOPE - every branch of the order-type chain carries the same unguarded calls: delivery_button (customer_id=='' ¦ customer_id=='1' ¦ address==''), dine_in¦vip¦club (waiter_id=='' ¦ customer_id==''), take_away (waiter_id=='' ¦ customer_id==''). Delivery was worst: it also refuses walk-in (customer_id=='1'), so a waiter on the default customer crashed there even WITH a customer selected. FIX: all 29 op1/op2 .open()/.close() calls made null-safe - identical behaviour where the dropdown exists, nudge skipped where it does not. 28 in the order paths (.place_order_operation, #direct_invoice); the 29th (.same_or_diff_state_modal) is the same crash class and was guarded too. An assertion caught that 29th site, which I would otherwise have missed. VERIFIED (measured, not inferred) - waiter session, register open, item in cart. BEFORE (pre-fix script restored, order type forced at attribute level because the counter lock stops a waiter switching it in the UI): Regular/Outlet/Delivery/VIP/Club with no customer -> TypeError, 0 requests; Delivery+walk-in -> TypeError, 0 requests. AFTER, each on a FRESH page load: Regular, Outlet, VIP, Club and Delivery+real customer all -> no crash, POST Sale/add_kitchen_sale_by_ajax fires; Delivery+walk-in -> no crash, refuses cleanly (correct - walk-in is not a valid delivery customer). METHOD NOTE: my first matrix was INVALID and I caught it before reporting - selected_ok was false on 4 of 5 rows, meaning the order type never actually switched and all five trials re-ran the same branch; and a later single-page run was contaminated by state left by the previous trial, so the final matrix uses one fresh page load per order type. RULED OUT: register gate (waiter loaded the POS with registers open at the outlet - and it fails loudly, redirecting away from the POS entirely), zero-stock block (only in add-to-cart paths, and it fails open), server guards (they return an invoice_msg the app displays, so they cannot produce silence). DEPLOY: commit a968d3e1 - pos_script_v7.3.js plus main_screen.php carrying the ?v=3.5->3.6 cache bust IN THE SAME COMMIT; without that bump tills keep the broken cached script.
Cleanup | Category icon filenames contain spaces (Beer Mug.png, etc.) | Logged - not scheduled | Low | Flagged during the UI redesign, deliberately not fixed. Several icon assets are named with spaces. They work because the browser percent-encodes the space, but such names break naive URL building, some cache/CDN layers, and unquoted shell handling. Rename to hyphenated lowercase AND update references in one change - renaming the files alone breaks the pages pointing at them.
Redesign | [Regression - FOUND AND FIXED] POS category grids lost their tile markup | Done - fixed and verified | High | Introduced by my own thumbnail patch, caught only when the redesign was click-tested through a real order flow. pos_thumb_fix.py sliced out a region ending at '$menu_to_show .= $ir_thumb;' then tried to re-emit the <img> with a .replace() on that same string; the slice had consumed it, so the replace matched nothing and SILENTLY no-oped. Lost: the <div class=single_item> wrapper (data-price*, id=item_N), the <img>, and the $food_menu_tooltip/$item_name_c block, leaving an orphaned </div>. Live effect: the default grid still worked (JS-built from window.items) but clicking ANY category rendered bare name/price text, no image, NOT clickable. Same silent-no-op mode as the userHome.php menu-list break: a .replace() whose match may already be consumed now requires an assertion. After fix: 197 tiles, 197 images, 33 holders, 0 notices.
Next | [Base-product] Mobile category rail opens on CSS :hover only | Logged - not scheduled | Low | Found while click-testing the redesign at 375x812. The mobile category surface (.all__menus, toggled by .show_all_menu) reveals categories via '.it_has_children:hover .sub_menu' (style2.css:2523). Hover does not exist on touch, so on a waiter tablet those categories may be unreachable. Vendor behaviour, NOT caused by the redesign, and NOT verified on real touch hardware - flagged only. Desktop rail unaffected (33/33 clickable, light and dark).
Redesign | Dark theme rebuilt to match the supplied mockup (POS + dashboard) | Done - verified | Medium | User feedback on the first dark pass: category buttons too rounded, too much white. Root cause of the white: the first pass themed the CONTENT of the sale screen but not the PANELS - style2.css paints .main_left/.main_middle/.main_right/.main_center/.holder/.top_header_part a hardcoded #fff. Added theme sections 15-21. Category radius 9px->4px. All painted FROM TOKENS so light is unchanged (--rx-surface IS #fff in light) - re-measured light after the change and every surface matched. Separators use inset box-shadow, never border, so no element gains box size. RESULTS: POS on-screen light surfaces 23->2 (both intentional brand greens); low-contrast text 9->4 (the 4 remaining are white-on-brand pills identical in LIGHT too, i.e. pre-existing). Dashboard: 11 white KPI slabs -> 0 light surfaces, 0 low-contrast, charts intact. CHART FIX: the dashboard loads TWO Chart.js builds (v3 then v2, v2 overwriting window.Chart), so Chart.getChart() was undefined and my retint was a silent no-op; the vendor also sets borderColor '#00000000' and defines no scales at all. Chart now hands its instance to the theme layer. Hit-testing re-run after the CSS: 19/19 categories, 12/12 tiles, 2/2 order buttons, 6/6 operation buttons, IDENTICAL with the theme on and off.
Incident | [CRITICAL - FIXED] Second waiter crash: .select2('data') on hidden waiter field | Done - fixed and verified | Critical | FOLLOW-UP to row 73. The v3.6 fix was real but INCOMPLETE, and my verification of it was flawed. v3.6 guarded .data('select2') results (op1/op2, 29 sites, all still correct). This is a DIFFERENT select2 API on the same element - .select2('data') - at three sites sitting EARLIER in the same handler, so the click died at line 8479 and never reached the guarded code at 8530+. Error: "Uncaught TypeError: Cannot read properties of undefined (reading 'data')", preceded by select2's own warning "The select2('data') method was called on an element that is not using Select2". No order request ever reached the network. WHY MY v3.6 TESTING MISSED IT - the view and the JS branch on two DIFFERENT flags: the view renders #select_waiter as a hidden input when $is_waiter_user (isWaiterUser() = session designation=='Waiter' OR is_waiter=='Yes'), while the JS called .select2('data') when waiter_app_status!='Yes', and main_screen.php:5 sets $waiter_app_status = session is_waiter. So a waiter with designation 'Waiter' but is_waiter NOT 'Yes' gets the hidden input AND takes the select2 path. My test session set is_waiter='Yes', which took the safe else branch and hid the bug; production waiters have is_waiter='No'. THE FLAG MISMATCH IS THE REAL DEFECT - the crash is only its symptom. LESSON: my test fixture was built to satisfy the feature's own happy path rather than to match production, so it validated the wrong shape. FIX: new irWaiterName() helper tests the ELEMENT, not a flag - uses .select2('data') only when #select_waiter really is a select carrying a select2 instance, else reads #select_waiter_name (which the view always emits beside the hidden input). Applied at all three sites: 8479 (.place_order_operation, was guarded by the WRONG flag), 9023 (#direct_invoice, completely unguarded), 9711 (split payment, completely unguarded). The latter two had no flag check at all and so crashed for ANY waiter. VERIFIED on the production session shape (designation=Waiter, is_waiter=No, hidden INPUT, waiter_app_status renders 'No'), user's exact steps - Cup Yogurt, total 3000.00, Place Order: v3.6 -> TypeError reading 'data', 0 order requests; v3.7 -> no error, POST Sale/add_kitchen_sale_by_ajax fires. Admin regression same build: no crash, waiter dropdown still opens (select2-container--open=2), so behaviour unchanged where a real select2 exists. DEPLOY: commit 48936b4e - pos_script_v7.3.js + main_screen.php carrying ?v=3.6->3.7 in the SAME commit.
Register | Admin Register Management - force-close a register on someone else's behalf | Done - verified | High | Admin/Manager screen listing every open register across accessible outlets, with a force-close that reconciles a register abandoned by whoever opened it. DESIGN DECISIONS (user-confirmed before build): (1) the admin must TYPE the actually-counted cash, shown beside the system-computed figure - never a one-click accept, or the close stops catching discrepancies, which is its whole purpose; (2) calculation window is the register's own opening time to the moment of the click, same as a normal close, no backdating; (3) accountability is recorded - who force-closed, when, whose register, and why; (4) the discrepancy is stored in DEDICATED COLUMNS (system_closing_balance, force_closed_by, force_close_reason) rather than only as audit-log prose, given what it protects. REUSE: the arithmetic lives in Sale::closeRegister() plus six Sale_model methods that read counter_id/outlet_id from the SESSION, so they cannot compute for someone else's register. Added seven parameterised *ForRegister() twins taking counter_id/outlet_id explicitly, SQL byte-identical to the originals; the originals were left untouched so the normal per-user close is unaffected. Race guarded by WHERE id=? AND register_status=1 with an affected_rows() check. THREE PRE-EXISTING BUGS FOUND BY ACTUALLY RUNNING IT, not by reading it: (a) getAccessibleOutletIds() leaked an unterminated CI3 query-builder chain into its next query, so ANY non-Admin caller hit "Column 'id' in field list is ambiguous" - fixed with reset_query(); (b) the Register controller never loaded Sale_model; (c) the new JS called toastr, which userHome.php does not load (only the POS layout does) - switched to swal after confirming the bundled library is really SweetAlert v1. MENU/VERIFICATION LESSON - THE EXPENSIVE PART: the user could not see the menu item for several rounds while I reported it verified. Both claims were true and both missed each other: the <li> really was in userHome.php, and my DOM proof was real - but it was run against the SCRATCH database with the migration applied, while the user was looking at PRODUCTION, where it was not. Menu items are filtered client-side by user_home_buttom.js against window.menu_objects, built from the session's function_access, which is snapshotted from tbl_access AT LOGIN - so with no tbl_access row the entry is stripped from the DOM for everyone including Admin, and re-login cannot help because the row it reads does not exist. The same missing row also emptied the role-permission checkbox, which the user reported as a second symptom; it was the same cause. LESSON: 'verified' must name the database it was verified against, and a component proof on scratch is not evidence about production. RESOLUTION: migration applied to live 2026-09-04 after a mysqldump of tbl_register/tbl_access/tbl_role_access (db/backups/, gitignored) - tbl_access id 381, granted to Admin+Manager, 3 nullable columns added, register rows 24 before and after. Menu placement then changed twice on request: out of the Report submenu to a standalone top-level item above Report, plus an Admin-only header button beside the light/dark switch. The header button is gated by a DIRECT role check rather than data-access/menu_assign_class, matching the existing todays_summary button, so it does not depend on tbl_access or on re-login; the controller still gates the route via checkAccess(). Verified with the permission row deleted to mirror production exactly: button visible, sidebar entry correctly still hidden. User confirmed end-to-end on their own live account: 'tested ok'. DEPLOY: commits 84a0f165 (feature) and ef75e0ec (menu placement).
Redesign | POS category rail - 3D depth, larger wrapping labels (client visual request) | Done - verified | Medium | Client compared the live rail against the originally approved reference and asked for more 3D depth and BIGGER buttons - explicitly taller, not wider. Delivered in two rounds. ROUND 1 offered two variants behind a ?rxcat= switch so the client could compare on their own till against the reference image, since this is a subjective visual call: v1 raised/42px, v2 bold/53px. Measured in-browser at 1440x900 against the rail's real calc(100vh - 120px) box: width stayed 130px in both (the brief's hard constraint - .list-of-item is a fixed column, so nothing outside the rail moves), heights 30 -> 42 -> 53, categories visible before scrolling 22 -> 16 -> 13 of 23. A third variant that wrapped labels was built and CUT: it overshot to 77px because the longest names take three lines at 130px, leaving only 9 visible. ROUND 2 - client picked v2, and separately lifted the single-line constraint: wrapping is preferred over truncation. So labels went 15px/600 -> 17px/800 with white-space:normal, the ellipsis and nowrap from style2.css:399 overridden, and NO line-clamp, so a button grows to fit its name rather than the name being cut to fit the button. Height became a 56px FLOOR rather than a fixed value. FONT TRAP CAUGHT: the app's base Montserrat @import (style.css:2) loads 300-700 only, so the requested weight 800 would have rendered as a synthesised fake-bold. Added an explicit 800 link in main_screen.php - same family and host, so it adds a weight rather than another typeface. DEPTH RECIPE: three parts, not one shadow - a solid inset bottom edge reading as the button's thickness, an outer cast shadow lifting it off the rail, and an inset top highlight so the face looks lit from above; :active collapses the edge by its own thickness so the press reads as physical. The sheen is background-IMAGE, which layers over the per-category background-color set by the data-cix rules without restating eight colours per rule. TRADE ACCEPTED KNOWINGLY: taller buttons mean fewer categories reachable without scrolling. This supersedes the deliberate height decision in theme section 16; that comment is now marked superseded rather than deleted, so the original reasoning is not lost. Client confirmed the trade twice. Round 1 measured 13 of 23; round 2's larger text pushes it to roughly 11-12, which was flagged to the client as a CHANGE from the number they signed off rather than reported as still 13 - the final figure is calculated, not measured, because browser navigation to the local server was blocked during round 2. Side benefit worth keeping: at a 56px floor every button clears the 44px minimum normally recommended for a touch target; the old 30px rail did not, so this is a handling improvement and not only cosmetic. PROCESS NOTE: a sed one-liner used for the CSS cache-buster silently converted userHome.php from CRLF to LF, turning a 1-line change into a 2344-line diff. Caught with git diff --ignore-cr-at-eol before committing, reverted, and re-applied with an editor that preserves the file's bytes. Worth remembering on this repo - its files are not uniformly LF. PREVIEW ARTIFACT: claude.ai/code/artifact/22a01b29-7703-4814-b04d-677f2f8ae727 - renders the before/after at true 130px size from the same CSS values and typeface as the committed theme. DEPLOY: commit f76a2106, theme section 22, cache-buster v7.7.1.
Phase B | POS Sale screen - Food / Drinks toggle, Search button, search clears ("Part B") | Done - built and live | Medium | Delivered 2026-09-15. The roadmap (line 297) still carries the note "Local only; not on live", which is stale - both clients are well past that commit. 18/18 regression suite, referenced throughout doc/HOTEL_ADDON_PLAN.md as the Part B baseline.
Phase B | Table-first ordering flow | Done - built and live | High | Migration 2026-09-15_04_table-first-flow.sql. Plan and decisions in doc/TABLE_FIRST_FLOW_PLAN.md. Tables panel regression 55/22/28/16. Was never given a tracker row.
Report | Waiter's Register Report - one waiter's own takings for one register session | Done - NOT YET DEPLOYED | Medium | Built 2026-09-25. Filtered view of the Register Report plus the waiter's voided/cancelled orders from tbl_audit_logs, a completed-orders list and a print button. Reached from the Report menu and the waiter panel. Needs migration 2026-09-25_01_waiter-register-report.sql on each client. Commits 30e17af5, 54ca0cfd, 38e0a894, 6383ab7b. Waiters must log out and back in to pick up the permission.
Sync | S7 - two-way merge between the local server and the online copy | Built - never run against live data | High | Deployment Manager gained a merge engine: orders, their edits and voids, running orders to the kitchen screen, customers matched on phone, catalogue push. Insert-only; only the side that created an order may change it; nothing is ever deleted. 144 checks pass on practice databases and the readiness check passes against the real Rockbell host. THE FIRST REAL MERGE HAS NOT BEEN RUN. Do it on a quiet morning, watched, after confirming the live backup.
Perf | Local server optimisation - no internet fetches, no animation delay | Done - NOT YET DEPLOYED | High | Core pages were fetching fonts from fonts.googleapis.com (measured 1.43s, render-blocking, and a stall at a venue with no internet) - now served locally. Page preloader wasted a full second after load; jQuery.fx off, animate.css forced to 0s. Login measured 0.82s end to end, 12 requests, none external. Commit b43816a2. Machine config (php.ini OPcache, my.ini) does NOT deploy - see Technical Guide v2.8 "Production Server Setup Checklist".

## Legend
Priority Color Legend
Critical | Security holes, data integrity bugs, anything touching live/real data — needs immediate attention
High | Core features, blocking issues, major architectural decisions
Medium | Important but not urgent — real value, no immediate risk
Low | Cosmetic, nice-to-have, or deliberately deferred by choice